## Tracker
ACRE Partners |  |  | Adventures In CRE - Development Tracker - Version 1.0
Project Commencing On | 2016-11-01 |  | Author: Michael Belasco
To be Completed By | 2017-08-01 |  | Email: BelascoCRE@Gmail.com
Divided Sky Hotel | [70 empty] | Delete Rows
2017-08-01 | time axis 2016-11-01 to 2021-10-01
Task | Milestone? | Dependent Upon | Independent Start Month (select 'Nothing' in Column D) | If Dependent, Starts Plus or Minus X Months From Finish | Duration | Dependent Start Month | Start Month | Start | End Month | Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Yes
Nothing | No
Close On Land | Yes | Nothing | 1 | 5 | 1 | 4 | 1 | 2016-11-01 | 1 | 2016-11-01 | [61 empty] | Close On Land | bar: 2016-11-01 to 2021-10-01
50% Schematic Design | No | Close On Land |  | 1 | 3 | 2 | 2 | 2016-12-01 | 4 | 2017-02-01 | [61 empty] | 50% Schematic Design
Zoning and Land Use Acception Applications Prepared | No | 50% Schematic Design |  | 0 | 1 | 4 | 4 | 2017-02-01 | 4 | 2017-02-01 | [61 empty] | Zoning and Land Use Acception Applications Prepared
Submit 50% SD Design Package and Legal Apps to Planning | Yes | 50% Schematic Design |  | 1 | 1 | 5 | 5 | 2017-03-01 | 5 | 2017-03-01 | [61 empty] | Submit 50% SD Design Package and Legal Apps to Planning | bar: 2016-11-01 to 2021-10-01
Begin Community Outreach | No | Submit 50% SD Design Package and Legal Apps to Planning |  | 0 | 3 | 5 | 5 | 2017-03-01 | 7 | 2017-05-01 | [61 empty] | Begin Community Outreach
Community Meeting #1 | No | Submit 50% SD Design Package and Legal Apps to Planning |  | 0 | 1 | 5 | 5 | 2017-03-01 | 5 | 2017-03-01 | [61 empty] | Community Meeting #1
Community Meeting #2 | No | Community Meeting #1 |  | 2 | 1 | 7 | 7 | 2017-05-01 | 7 | 2017-05-01 | [61 empty] | Community Meeting #2
Planning Review Period | No | Submit 50% SD Design Package and Legal Apps to Planning |  | 0 | 6 | 5 | 5 | 2017-03-01 | 10 | 2017-08-01 | [61 empty] | Planning Review Period
100% Schematic Design | No | 50% Schematic Design |  | 1 | 4 | 5 | 5 | 2017-03-01 | 8 | 2017-06-01 | [61 empty] | 100% Schematic Design
Planning Board Meeting | Yes | Planning Review Period |  | 0 | 1 | 10 | 10 | 2017-08-01 | 10 | 2017-08-01 | [61 empty] | Planning Board Meeting | bar: 2016-11-01 to 2021-10-01
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Insert Row
Go to Delete Rows
Return
Delete Row
Delete Row
Delete row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row
Delete Row

## Print
ACRE Partners
Project Commencing On | [7 empty] | 2016-11-01
To be Completed By | [7 empty] | 2017-08-01
Divided Sky Hotel
2017-08-01 | time axis 2016-11-01 to 2021-10-01
Task | Milestone? | Dependent Upon | Independent Start Month (select 'Nothing' in Column D) | If Dependent, Starts Plus or Minus X Months From Finish | Duration | Dependent Start Month | Start Month | Start | End Month | Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Yes
Nothing | No
Close On Land | Yes | Nothing | 1 | 5 | 1 | 4 | 1 | 2016-11-01 | 1 | 2016-11-01 | bar: 2016-11-01 to 2021-10-01
50% Schematic Design | No | Close On Land |  | 1 | 3 | 2 | 2 | 2016-12-01 | 4 | 2017-02-01
Zoning and Land Use Acception Applications Prepared | No | 50% Schematic Design |  | 0 | 1 | 4 | 4 | 2017-02-01 | 4 | 2017-02-01
Submit 50% SD Design Package and Legal Apps to Planning | Yes | 50% Schematic Design |  | 1 | 1 | 5 | 5 | 2017-03-01 | 5 | 2017-03-01 | bar: 2016-11-01 to 2021-10-01
Begin Community Outreach | No | Submit 50% SD Design Package and Legal Apps to Planning |  | 0 | 3 | 5 | 5 | 2017-03-01 | 7 | 2017-05-01
Community Meeting #1 | No | Submit 50% SD Design Package and Legal Apps to Planning |  | 0 | 1 | 5 | 5 | 2017-03-01 | 5 | 2017-03-01
Community Meeting #2 | No | Community Meeting #1 |  | 2 | 1 | 7 | 7 | 2017-05-01 | 7 | 2017-05-01
Planning Review Period | No | Submit 50% SD Design Package and Legal Apps to Planning |  | 0 | 6 | 5 | 5 | 2017-03-01 | 10 | 2017-08-01
100% Schematic Design | No | 50% Schematic Design |  | 1 | 4 | 5 | 5 | 2017-03-01 | 8 | 2017-06-01
Planning Board Meeting | Yes | Planning Review Period |  | 0 | 1 | 10 | 10 | 2017-08-01 | 10 | 2017-08-01 | bar: 2016-11-01 to 2021-10-01
Adventures In CRE - Development Tracker - Version 1.0
Author: Michael Belasco
www.AdventuresInCRE.Com
Email: BelascoCRE@Gmail.com